## Number per screens
Msapp status on Tests (06/11/2012)
Commented screens |  | Status on reported 'Bugnet'
Screens | Nb Bugnet |  | OPEN |  | CLOSED |  | ALL
Anthrop | 8 | Type | N | % | N | % | N | %
Brand | 3 | Evolution | 21 | 26.5823 | 2 | 2.3256 | 23 | 13.9394
Checklist | 7 | Bug | 42 | 53.1646 | 70 | 81.3953 | 112 | 67.8788
EPICTEXT | 5 | Invalid | 2 | 2.5316 | 0 | 0 | 2 | 1.2121
Nut Limit | 1 | Note | 2 | 2.5316 | 5 | 5.814 | 7 | 4.2424
Nutrient | 2 | Q&A | 7 | 8.8608 | 9 | 10.4651 | 16 | 9.697
Param ES | 2 | To be affected | 5 | 6.3291 | 0 | 0 | 5 | 3.0303
Substit | 3 | Total | 79 |  | 86 |  | 165
RawToCook | 1
SpDiet | 1
FCO | 1 | Owner by
Probing | 6
Interviewer | 7 | Name | N | %
Classif | 33 | Corinne | 54 | 32.7273
Facets/descriptors | 27 | P&G Grange | 75 | 45.4545
Food list | 2 | Gwenhael | 31 | 18.7879
HHM | 5 | Iteal | 5 | 3.0303
Maximum | 1 | Total | 165
Std Unit | 1
Photo | 5
Thickness | 1
Translation GUI | 1
22 screens (123 bugnets) from 74 total Food screens
Gal | 31
Menu | 4
35 General bugnets
Other (Bugnet app) | 2
Iteal | 5
165

## Open Bugnet
Id | Order | Title | Votes | Category | Creator | Owner | Assigned | Type | Milestone | Affected Milestone | Status | Priority | Created | Last Update | Last Update User
e-SMP-3564 | Antropometric | [MS > Library Data] Antropometric page management | 4 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3553 | Bugnet | Bugnet management - timeout | 3 | Others | Gabriel | Gabriel | Administrator | Q&A | none | none | Open | Normal | 10/30/2012 | 10/30/2012 | Gabriel
e-SMP-3454 | Checklist | Checking FCO list : too much time for a few entries... [LEVEL Library] | 7 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | Open | High | 10/14/2012 | 10/28/2012 | Philippe
e-SMP-3480 | Checklist | Checklist by FCO: FCO code + label | 2 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3484 | Checklist | Checklist by FCO: FICHE | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3398 | Classif | MS Food classification - Liste: Fold/unfold option | 3 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3399 | Classif | MS Food classification - Liste: Folded-unfolded display | 8 | Code | Corinne | Corinne | Corinne | Bug | none | none | WIP | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3400 | Classif | MS Food classification - Liste: Group code display | 6 | Code | Corinne | Corinne | Corinne | Evolution | Minor | none | Open | High | 10/1/2012 | 10/3/2012 | Tuan Anh
e-SMP-3401 | Classif | MS Food classification - Liste: The tooltip œStatus  | 9 | none | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | High | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3402 | Classif | MS Food classification - Liste: Display time & question | 3 | none | Corinne | Corinne | none | Bug | none | none | Open | High | 10/1/2012 | 10/1/2012 | Corinne
e-SMP-3404 | Classif | MS Food classification - Fiche: Presentation | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3405 | Classif | MS Food classification - Functions: Add a group | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3406 | Classif | MS Food classification - Functions: Add and default | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | High | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3408 | Classif | MS Food classification - Functions: Delete | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3413 | Classif | MS Food classification - Functions: Mass translation & status | 7 | Code | Corinne | Corinne | Corinne | Evolution | none | none | Open | Urgent | 10/1/2012 | 10/19/2012 | Administrator
e-SMP-3416 | Classif | MS Food classification - Functions: Mass translation & Pagination | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3417 | Classif | MS Food classification - DATABASE: MS_Classification & MS_Classification_L10N | 8 | Code | Corinne | Corinne | esmp | Evolution | SIGNF | none | To be Affected | Urgent | 10/1/2012 | 10/16/2012 | gwenhael
e-SMP-3419 | Classif | MS Food classification - DATABASE: Questions on Classification | 6 | Code | Corinne | Corinne | Corinne | Note | none | none | Open | Normal | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3516 | Classif | Classification screens at PROJECT and COUNTRY level | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | WIP | Urgent | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3517 | Classif | Classification screens at PROJECT and COUNTRY level: Special approach for sub-sub-groups | 4 | Code | Corinne | Corinne | gwenhael | Evolution | OPER | none | WIP | Urgent | 10/26/2012 | 10/31/2012 | Tuan Anh
e-SMP-3528 | Classif | [MS > Library data>CLASSIFICATIONS > Food Classification] Deletation summary | 5 | Design / GUI | Gabriel | Gabriel | duydt | Bug | SIGNF | none | Re-Openned | Normal | 10/28/2012 | 11/5/2012 | Tuan Anh
e-SMP-3533 | Classif | FOOD CLASSIFICATION ITEM : error creating food classification | 6 | Code | Philippe | Philippe | Nguyen Xuan Hiep | Bug | OPER | none | Open | Normal | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3535 | Classif | Food classification : copy from a level to an other. | 3 | Code | Philippe | Philippe | gwenhael | Bug | none | none | Open | Normal | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3561 | Classif | [MS > project perimeter ] Adding food classification | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3573 | Classif | MS Food classification: sheet refresh | 2 | Code | Corinne | Corinne | Tuan Anh | Bug | none | none | Open | Normal | 11/6/2012 | 11/6/2012 | Corinne
e-SMP-3504 | Facets/descriptors | Facets & descriptors : fiche & Group field | 3 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Open | Normal | 10/25/2012 | 10/26/2012 | Tuan Anh
e-SMP-3506 | Facets/descriptors | Facets & descriptors : LISTE | 3 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | Normal | 10/25/2012 | 10/30/2012 | Corinne
e-SMP-3507 | Facets/descriptors | Facets & descriptors: Fiche & default for œMulti-selection of descriptors  field | 5 | Code | Corinne | Corinne | Corinne | Evolution | Minor | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3509 | Facets/descriptors | Facets & descriptors: List and add function | 5 | Code | Corinne | Corinne | Corinne | Bug | SIGNF | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3510 | Facets/descriptors | Facets & descriptors: Fiche descriptor &default for œwith limitation for ingredient ¦  field | 6 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3511 | Facets/descriptors | Facets & descriptors: Descriptor Fiche & œraw to cooked category  field | 5 | Code | Corinne | Corinne | Corinne | Bug | Minor | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3512 | Facets/descriptors | Facets & descriptors: Descriptor Fiche & descriptor Type field | 4 | Code | Corinne | Corinne | Corinne | Q&A | none | none | Open | Normal | 10/25/2012 | 10/26/2012 | Tuan Anh
e-SMP-3539 | Facets/descriptors | "Facet/descriptor list" screen at country level | 6 | Code | Corinne | Corinne | Corinne | Invalid | Minor | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3540 | Facets/descriptors | Facets/descriptors at Project level: Add new item function (green cross) | 5 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3541 | Facets/descriptors | Facets/descriptors at Library level: Error message | 6 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Urgent | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3542 | Facets/descriptors | Facets/descriptors at Library level: Buttons with work in Mass | 5 | Code | Corinne | Corinne | Tuan Anh | Evolution | OPER | none | WIP | Normal | 10/29/2012 | 11/6/2012 | Corinne
e-SMP-3543 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: add function and field Facets-Descriptors | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3544 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: Add button | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3545 | Facets/descriptors | Facet/descriptor list at Project level: Non validated Facets and attached descriptors | 5 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3546 | Facets/descriptors | Facet/descriptor at Project level - Fiche | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | WIP | Normal | 10/29/2012 | 10/31/2012 | Tuan Anh
e-SMP-3549 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: Liste/Fiche and order | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/30/2012 | 11/2/2012 | Tuan Anh
e-SMP-3565 | Facets/descriptors | [MS > project perimeter ] Add facets / descriptors | 5 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3426 | Gal | (design) deleting records | 6 | Others | gwenhael | gwenhael | esmp | Evolution | Minor | none | Open | Normal | 10/1/2012 | 10/16/2012 | gwenhael
e-SMP-3443 | Gal | [MS > Library Data] Abnormal default selection | 7 | Design / GUI | Gabriel | Gabriel | Corinne | Evolution | SIGNF | none | To be Affected | Normal | 10/9/2012 | 10/26/2012 | Tuan Anh
e-SMP-3474 | Gal | Blue cross function (Iport) | 3 | Spec | Corinne | Corinne | Corinne | Q&A | OPER | none | To be Affected | Normal | 10/19/2012 | 10/31/2012 | Tuan Anh
e-SMP-3479 | Gal | Function blue cross and pagination | 5 | Spec | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3481 | Gal | Control button | 5 | Code | Corinne | Corinne | Corinne | Note | none | none | Reviewed | Normal | 10/21/2012 | 10/26/2012 | Tuan Anh
e-SMP-3482 | Gal | MASS translation - Column Sort | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/22/2012 | Tuan Anh
e-SMP-3483 | Gal | MASS translation - Default Status | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3490 | Gal | Tooltip for Status: missing labels | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/22/2012 | 10/25/2012 | Tuan Anh
e-SMP-3491 | Gal | Import data / Import Table: Proposed Perimeter | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Open | Normal | 10/22/2012 | 10/24/2012 | gwenhael
e-SMP-3494 | Gal | Controls and export files | 2 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/23/2012 | 10/23/2012 | Tuan Anh
e-SMP-3515 | Gal | Info column in all lists and some pop-up | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | WIP | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3519 | Gal | [(Food screens)] classification independent sort | 4 | Code | gwenhael | gwenhael | gwenhael | Evolution | OPER | none | Open | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3520 | Gal | [(Food screens)] classification selection | 4 | Spec | gwenhael | gwenhael | gwenhael | Evolution | Minor | none | Open | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3529 | Gal | [MS > Library Data] Input problem with International labels | 5 | Design / GUI | Gabriel | Gabriel | Nguyen Xuan Hiep | Bug | SIGNF | none | Open | Urgent | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3547 | Gal | Project data and Refresh / Country data and refresh | 5 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3550 | Gal | [(Food screens)] classification column should be foldable | 5 | Spec | gwenhael | gwenhael | gwenhael | Evolution | Minor | none | WIP | Normal | 10/30/2012 | 10/31/2012 | Tuan Anh
e-SMP-3560 | Gal | [MS > library perimeter ] Mass translation management | 4 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | High | 11/4/2012 | 11/5/2012 | Nguyen Xuan Hiep
e-SMP-3567 | Gal | [IM > scroll bar] Problem with mouse wheel | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/6/2012 | Tuan Anh
e-SMP-3569 | Gal | [MS > GUI] Page management | 5 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Q&A | OPER | none | Reviewed | Low | 11/4/2012 | 11/5/2012 | Do Hang
e-SMP-3570 | Gal | [MS] mail management | 2 | Others | Gabriel | Gabriel | gwenhael | Q&A | SIGNF | none | Open | High | 11/4/2012 | 11/4/2012 | Gabriel
e-SMP-3562 | HHM | [MS > Library Data] HHM error management | 4 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3563 | HHM | [MS > country perimeter ] Country code management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | WIP | Normal | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3487 | Interviewer | Interviewer: Fiche & region | 4 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/22/2012 | 10/23/2012 | Tuan Anh
e-SMP-3488 | Interviewer | Interviewer list: Unicity | 5 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/22/2012 | 11/2/2012 | Tuan Anh
e-SMP-3489 | Interviewer | Interviewer: Serach | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | WIP | Normal | 10/22/2012 | 10/23/2012 | Tuan Anh
e-SMP-3557 | Interviewer | [MS > country perimeter ] Interviewer management | 2 | Others | Gabriel | Gabriel | Gabriel | Bug | Minor | none | Open | Low | 11/4/2012 | 11/5/2012 | gwenhael
e-SMP-3558 | Interviewer | [IM > Country perimeter] Focus problem creating Interviewer record | 3 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3559 | Interviewer | [MS > country perimeter ] Interviewer page management | 4 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | Urgent | 11/4/2012 | 11/5/2012 | duydt
e-SMP-3486 | Menu | Menu scrollbar | 4 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/22/2012 | 10/26/2012 | Tuan Anh
e-SMP-3572 | Param ES | GUI : EpicSoft Parameters. | 6 | Design / GUI | Philippe | Philippe | Tuan Anh | Bug | OPER | none | Reviewed | Normal | 11/4/2012 | 11/5/2012 | Do Hang
e-SMP-3526 | Photo | [MS > Library data> PHOTOS ] Update photo serie record | 4 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | WIP | Normal | 10/28/2012 | 10/30/2012 | Tuan Anh
e-SMP-3566 | Photo | [MS > Library Data] Photo management | 6 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | High | 11/4/2012 | 11/5/2012 | duydt
e-SMP-3568 | Photo | [MS > library perimeter ] Silverlight crash when creating a big serie of photos | 4 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/6/2012 | duydt
e-SMP-3449 | Probing | Insert probing : from 2 seconds to 1 minut to commit one probing. | 5 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | WIP | Normal | 10/14/2012 | 10/17/2012 | Tuan Anh
e-SMP-3508 | RawToCook | Raw to Cook Gategory screen: Same values twice | 4 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/25/2012 | 10/31/2012 | Tuan Anh
e-SMP-3556 | Substit | [MS > Project perimeter / Add subtituable record ] Abnormal records | 5 | Code | Gabriel | Gabriel | Gabriel | Invalid | SIGNF | none | WIP | High | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3571 | Translation GUI | [SC > Administration ] Language management | 4 | Others | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | WIP | Low | 11/4/2012 | 11/5/2012 | Tuan Anh

## Closed Bugnet
Id | Order | Title | Votes | Category | Creator | Owner | Assigned | Type | Milestone | Affected Milestone | Status | Priority | Created | Last Update | Last Update User
e-SMP-2675 | Iteal | Need to update MS_PROBQUE table. | 2 | Spec | hieuphan | hieuphan | Tuan Anh | Evolution | OPER | none | Closed | High | 2012-06-04 | 5/4/2012 | Tuan Anh
e-SMP-2682 | Iteal | MS-NUTLIMIT: bugs in spec | 3 | Spec | duydt | duydt | duydt | Bug | OPER | none | Closed | High | 2012-06-04 | 6/13/2012 | Tuan Anh
e-SMP-2882 | Iteal | Rawcook | 2 | Code | Tuan Anh | Tuan Anh | Tuan Anh | Q&A | OPER | none | Closed | Urgent | 2012-05-05 | 10/19/2012 | Administrator
e-SMP-3310 | Iteal | MSapp_screen_Improb_descriptors - Rule 8 | 2 | Spec | Tuan Anh | Tuan Anh | Tuan Anh | Q&A | OPER | none | Closed | High | 2012-03-07 | 7/3/2012 | Tuan Anh
e-SMP-3397 | Classif | MS Food classification â€“ Liste: Sort Order | 7 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Closed | Urgent | 10/01/2012 | 10/19/2012 | Administrator
e-SMP-3403 | Classif | MS Food classification â€“ Fiche: Pop-up â€˜Parent groupâ€™: | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Closed | Urgent | 10/01/2012 | 10/14/2012 | Gabriel
e-SMP-3407 | Thickness | [Library > Photos > Thickness] exception | 4 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3409 | HHM | [Library > Photos > HHM] conflicting mandatory fields | 4 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3410 | HHM | [Library > Photos > HHM] missing fraction data | 2 | Others | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3411 | Classif | MS Food classification â€“ Functions: Export | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Closed | Urgent | 10/01/2012 | 10/10/2012 | gwenhael
e-SMP-3412 | Photo | [Library > Photos > Photos Series] superfluous check | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3414 | Classif | MS Food classification â€“ Functions: Mass translation & Column order | 6 | Code | Corinne | Corinne | gwenhael | Bug | none | none | Closed | High | 10/01/2012 | 10/16/2012 | gwenhael
e-SMP-3418 | Facets/descriptors | [Library > FACETS/DESCRPTORS > Facets] can't validate fiche | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3420 | Nut Limit | [Library > SETTINGS > Internal parameters > Nutrients limitations] Missing values for Unit and Name | 3 | Others | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3421 | Anthrop | [Library > SETTINGS > Anthropometric] typo | 6 | Others | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/01/2012 | 10/16/2012 | gwenhael
e-SMP-3422 | Nutrient | [Library > SETTINGS > Internal parameters > Nutrients list] Missing values for Unit | 2 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3423 | Classif | [Library > CLASSIFICATIONS > Food] pagination | 7 | Others | gwenhael | gwenhael | gwenhael | Q&A | Minor | none | Closed | Normal | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3424 | Gal | (design) focus in forms | 4 | Others | gwenhael | gwenhael | gwenhael | Note | OPER | none | Closed | Normal | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3425 | Gal | (design) downloading files | 5 | Others | gwenhael | gwenhael | gwenhael | Note | Minor | none | Closed | Low | 10/01/2012 | 10/8/2012 | gwenhael
e-SMP-3427 | Gal | (design) deleting records | 1 | Others | gwenhael | gwenhael | Tuan Anh | Q&A | Minor | none | Closed | Normal | 10/01/2012 | 10/1/2012 | gwenhael
e-SMP-3431 | SpDiet | [MS / Special diets] abnormal exception | 6 | Code | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/04/2012 | 10/9/2012 | Gabriel
e-SMP-3432 | Gal | [MS > Send Alert] Screen is fixed | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/05/2012 | 10/9/2012 | Gabriel
e-SMP-3433 | Bugnet | Bugnet management SCOPE2 | 2 | Code | Gabriel | Gabriel | Gabriel | Note | OPER | none | Closed | Normal | 10/05/2012 | 10/5/2012 | Gabriel
e-SMP-3434 | Classif | [Project > Clasification > Food] cannot remove | 6 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | High | 10/05/2012 | 10/16/2012 | gwenhael
e-SMP-3435 | Gal | (design) Send Alert: missing scrollbar in recipient list | 6 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/05/2012 | 10/16/2012 | gwenhael
e-SMP-3436 | Food list | [MS > Food Update] Abnormal error message | 7 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Closed | High | 10/05/2012 | 10/28/2012 | Gabriel
e-SMP-3437 | Classif | [Country > Classification > Food] missing Add / Update/Edit / Delete functions | 8 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/08/2012 | 10/19/2012 | Administrator
e-SMP-3438 | Facets/descriptors | [Library > FACETS/DESCRPTORS > Facets] error on creation | 4 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/09/2012 | 10/16/2012 | gwenhael
e-SMP-3439 | Menu | [MS > Library Data] Menu problem with bulgarian user.. | 6 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/09/2012 | 10/26/2012 | gwenhael
e-SMP-3442 | Nut unit | Problem with Nutrient unit. | 5 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | Closed | Normal | 10/09/2012 | 10/25/2012 | Philippe
e-SMP-3444 | Food list | [MS / Food list] abnormal exception | 7 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/09/2012 | 10/16/2012 | gwenhael
e-SMP-3445 | Classif | [Project > Clasification > Food] bypass sub-sub-group creation property | 7 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | High | 10/10/2012 | 10/23/2012 | gwenhael
e-SMP-3446 | Fractions | (global) fraction management | 8 | none | gwenhael | gwenhael | gwenhael | Note | OPER | none | Closed | High | 10/11/2012 | 10/23/2012 | gwenhael
e-SMP-3447 | Probing | [Library > SETTINGS > Probings List] invalid type management | 4 | Spec | gwenhael | gwenhael | Tuan Anh | Bug | SIGNF | none | Closed | High | 10/11/2012 | 10/21/2012 | Gabriel
e-SMP-3448 | Probing | Type of probing... How to set correct values has Checklist | 3 | none | Philippe | Philippe | Philippe | Bug | none | none | Closed | High | 10/14/2012 | 10/25/2012 | Philippe
e-SMP-3450 | Probing | problem of page location when adding all probings... | 5 | Design / GUI | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/28/2012 | Philippe
e-SMP-3451 | Anthrop | ANTHROPOMETRIC : Order of queries is not logic | 4 | Design / GUI | Philippe | Philippe | gwenhael | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3452 | Anthrop | ANTHROPOMETRIC : Problem with Sex = NULL entries | 3 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/25/2012 | Philippe
e-SMP-3453 | FCO | FCO List : Problem modifying an entrie [LEVEL Livrary] | 6 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3455 | EPICTEXT | EPICTEXT : What is this query name * (only numeric) ? | 5 | Code | Philippe | Philippe | gwenhael | Bug | SIGNF | none | Closed | High | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3457 | EPICTEXT | EpicText : After 20 entries focus is set on the first page... | 5 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/23/2012 | Philippe
e-SMP-3458 | EPICTEXT | Epictext : Unique Key violation | 4 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3461 | Anthrop | [ MS - Anthropometric ] Add Anthropometric value (weight label missing) | 4 | Design / GUI | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3462 | Anthrop | [ MS - Anthropometric ] Filtering in Anthropometric management (weight is missing) | 6 | Design / GUI | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/14/2012 | 10/19/2012 | Administrator
e-SMP-3463 | Substit | Substit table : error after loading. | 7 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3464 | EPICTEXT | Epictext : error while loading... | 6 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3467 | Facets/descriptors | Facet : my first entrie. | 7 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/17/2012 | Philippe
e-SMP-3468 | Menu | all M&S screens not available | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/16/2012 | 10/23/2012 | gwenhael
e-SMP-3470 | Facets/descriptors | [ MS - library / FACETS/DESCRIPTORS>Facet ] Message using green cross to create new item | 8 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Urgent | 10/16/2012 | 10/23/2012 | Gabriel
e-SMP-3471 | Classif | [MS > Library Data > CLASSIFICATION>Food Classification] can't remove item | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/16/2012 | 10/23/2012 | Gabriel
e-SMP-3473 | Brand | [MS > Library Data] Brandname management | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/18/2012 | 11/4/2012 | Gabriel
e-SMP-3428 | Checklist | [Library > SETTINGS > FCO Checklist] mass translation not refreshed | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/2/2012 | 10/9/2012 | gwenhael
e-SMP-3475 | Facets/descriptors | [MS > Library data>FACETS DESCRIPTOR] Problem to add an item | 3 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/21/2012 | 10/23/2012 | Gabriel
e-SMP-3476 | Facets/descriptors | FACET & DESCRIPTOR : What is this zone [Raw cooked category] | 2 | Design / GUI | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/21/2012 | 10/28/2012 | Philippe
e-SMP-3477 | EPICTEXT | [MS > Library data>EpicText] Mass translation | 7 | Spec | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/21/2012 | 10/28/2012 | Gabriel
e-SMP-3478 | Photo | [MS > Library Data>PHOTOS] Mass update comment & status | 4 | none | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/21/2012 | 10/23/2012 | Gabriel
e-SMP-3485 | Gal | [(Food screens)] 'Filter' button in Filters popups | 7 | Design / GUI | gwenhael | gwenhael | gwenhael | Note | Minor | none | Closed | Low | 10/22/2012 | 10/26/2012 | gwenhael
e-SMP-3492 | Checklist | Checklist per FCO: liste and sort order | 5 | Design / GUI | Corinne | Corinne | Corinne | Evolution | none | none | Closed | Normal | 10/22/2012 | 10/23/2012 | gwenhael
e-SMP-3493 | Gal | [(Food screens)] groups becoming inactive | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/22/2012 | 10/23/2012 | gwenhael
e-SMP-3495 | Anthrop | ANTHROPOMETRIC : visibility problem. | 4 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Philippe
e-SMP-3496 | Probing | [MS > Library Data] Page management in probing screen | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3497 | Gal | [MS / framework ] keyboard management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3498 | Facets/descriptors | [ MS - library / FACETS/DESCRIPTORS BY GROUP ] Error message in PROJECT perimeter | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3499 | Brand | [MS > Brandname CSV import] Can't import file | 6 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/23/2012 | 11/4/2012 | Gabriel
e-SMP-3500 | Checklist | [ MS - Checklist per FCO / COUNTRY perimeter ] Import management | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/24/2012 | 10/28/2012 | Gabriel
e-SMP-3501 | Iteal | Combox: can not Alt +down | 2 | Code | Do Hang | Do Hang | Do Hang | Bug | Minor | none | Closed | Normal | 10/25/2012 | 10/25/2012 | Do Hang
e-SMP-3502 | Gal | [(Food screens)] default selection too wide | 6 | Spec | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3503 | Facets/descriptors | [Project > Facet/Descriptors] shouldn't be able to create facet | 7 | Spec | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3505 | Gal | (GUI) action bar' icons above list content | 7 | Design / GUI | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Normal | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3513 | Facets/descriptors | [MS > Library data>Facet/Descriptor by group] System hangs adding a new facets / descriptor | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/25/2012 | 11/4/2012 | Gabriel
e-SMP-3518 | Menu | (GUI) wrong content displayed | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/26/2012 | 11/5/2012 | gwenhael
e-SMP-3521 | Anthrop | ANTHOPOMETRIC : What is the sort order of the main list ? | 1 | Design / GUI | Philippe | Philippe | Tuan Anh | Bug | none | none | Closed | Normal | 10/28/2012 | 10/28/2012 | Philippe
e-SMP-3524 | Facets/descriptors | [MS > PROJECT level / Add facet descriptor] Anormal sort | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | Minor | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3525 | Brand | [MS > country level ] Add brandname record | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/28/2012 | 10/30/2012 | Gabriel
e-SMP-3527 | HHM | [MS > Library Data] HHM error management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3530 | Classif | [MS > Library data> Food Classification ] Space management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3531 | Classif | [MS > Library data> Food Classification ] Space management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 10/30/2012 | Gabriel
e-SMP-3532 | Gal | [MS > Library data> PROJECT perimeter ] Error message with import data | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3534 | Classif | [MS > Library data> Food Classification ] Validating a food classification | 4 | Code | Gabriel | Gabriel | Gabriel | Q&A | OPER | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3536 | Classif | [MS > Food classification] Adding food classification item in project level | 5 | Code | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3537 | Maximum | [MS > country perimeter / Add food maximum ] Max value management | 6 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Low | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3538 | Std Unit | [MS > country perimeter / tab management ] unknow screen management result (after "Standard unit" menu selection) | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3551 | Probing | [MS > Library data> Probing ] Mass translation over probing | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3552 | Interviewer | [MS > country perimeter ] Interviewer management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Low | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3554 | Substit | Substite Table : Level Library = Validated Nothing on project level. | 5 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/30/2012 | 11/4/2012 | Philippe
e-SMP-3555 | Checklist | [MS > country perimeter/ Checklist per FCO ] Mass translation management | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/30/2012 | 10/31/2012 | Gabriel

## ALL
Id | Order | Title | Votes | Category | Creator | Owner | Assigned | Type | Milestone | Affected Milestone | Status | Priority | Created | Last Update | Last Update User
e-SMP-3421 | Anthrop | [Library > SETTINGS > Anthropometric] typo | 6 | Others | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/01/2012 | 10/16/2012 | gwenhael
e-SMP-3451 | Anthrop | ANTHROPOMETRIC : Order of queries is not logic | 4 | Design / GUI | Philippe | Philippe | gwenhael | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3452 | Anthrop | ANTHROPOMETRIC : Problem with Sex = NULL entries | 3 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/25/2012 | Philippe
e-SMP-3461 | Anthrop | [ MS - Anthropometric ] Add Anthropometric value (weight label missing) | 4 | Design / GUI | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3462 | Anthrop | [ MS - Anthropometric ] Filtering in Anthropometric management (weight is missing) | 6 | Design / GUI | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/14/2012 | 10/19/2012 | Administrator
e-SMP-3495 | Anthrop | ANTHROPOMETRIC : visibility problem. | 4 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Philippe
e-SMP-3521 | Anthrop | ANTHOPOMETRIC : What is the sort order of the main list ? | 1 | Design / GUI | Philippe | Philippe | Tuan Anh | Bug | none | none | Closed | Normal | 10/28/2012 | 10/28/2012 | Philippe
e-SMP-3564 | Antrop | [MS > Library Data] Antropometric page management | 4 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3473 | Brand | [MS > Library Data] Brandname management | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/18/2012 | 11/4/2012 | Gabriel
e-SMP-3499 | Brand | [MS > Brandname CSV import] Can't import file | 6 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/23/2012 | 11/4/2012 | Gabriel
e-SMP-3525 | Brand | [MS > country level ] Add brandname record | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/28/2012 | 10/30/2012 | Gabriel
e-SMP-3433 | Bugnet | Bugnet management SCOPE2 | 2 | Code | Gabriel | Gabriel | Gabriel | Note | OPER | none | Closed | Normal | 10/05/2012 | 10/5/2012 | Gabriel
e-SMP-3553 | Bugnet | Bugnet management - timeout | 3 | Others | Gabriel | Gabriel | Administrator | Q&A | none | none | Open | Normal | 10/30/2012 | 10/30/2012 | Gabriel
e-SMP-3428 | Checklist | [Library > SETTINGS > FCO Checklist] mass translation not refreshed | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/2/2012 | 10/9/2012 | gwenhael
e-SMP-3492 | Checklist | Checklist per FCO: liste and sort order | 5 | Design / GUI | Corinne | Corinne | Corinne | Evolution | none | none | Closed | Normal | 10/22/2012 | 10/23/2012 | gwenhael
e-SMP-3500 | Checklist | [ MS - Checklist per FCO / COUNTRY perimeter ] Import management | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/24/2012 | 10/28/2012 | Gabriel
e-SMP-3555 | Checklist | [MS > country perimeter/ Checklist per FCO ] Mass translation management | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/30/2012 | 10/31/2012 | Gabriel
e-SMP-3454 | Checklist | Checking FCO list : too much time for a few entries... [LEVEL Library] | 7 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | Open | High | 10/14/2012 | 10/28/2012 | Philippe
e-SMP-3480 | Checklist | Checklist by FCO: FCO code + label | 2 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3484 | Checklist | Checklist by FCO: FICHE | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3397 | Classif | MS Food classification â€“ Liste: Sort Order | 7 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Closed | Urgent | 10/01/2012 | 10/19/2012 | Administrator
e-SMP-3398 | Classif | MS Food classification â€“ Liste: Fold/unfold option | 3 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3399 | Classif | MS Food classification â€“ Liste: Folded-unfolded display | 8 | Code | Corinne | Corinne | Corinne | Bug | none | none | WIP | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3400 | Classif | MS Food classification â€“ Liste: Group code display | 6 | Code | Corinne | Corinne | Corinne | Evolution | Minor | none | Open | High | 10/1/2012 | 10/3/2012 | Tuan Anh
e-SMP-3401 | Classif | MS Food classification â€“ Liste: The tooltip â€œStatusâ€ | 9 | none | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | High | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3402 | Classif | MS Food classification â€“ Liste: Display time & question | 3 | none | Corinne | Corinne | none | Bug | none | none | Open | High | 10/1/2012 | 10/1/2012 | Corinne
e-SMP-3403 | Classif | MS Food classification â€“ Fiche: Pop-up â€˜Parent groupâ€™: | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Closed | Urgent | 10/01/2012 | 10/14/2012 | Gabriel
e-SMP-3404 | Classif | MS Food classification â€“ Fiche: Presentation | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3405 | Classif | MS Food classification - Functions: Add a group | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3406 | Classif | MS Food classification â€“ Functions: Add and default | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | High | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3408 | Classif | MS Food classification â€“ Functions: Delete | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | High | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3411 | Classif | MS Food classification â€“ Functions: Export | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Closed | Urgent | 10/01/2012 | 10/10/2012 | gwenhael
e-SMP-3413 | Classif | MS Food classification â€“ Functions: Mass translation & status | 7 | Code | Corinne | Corinne | Corinne | Evolution | none | none | Open | Urgent | 10/1/2012 | 10/19/2012 | Administrator
e-SMP-3414 | Classif | MS Food classification â€“ Functions: Mass translation & Column order | 6 | Code | Corinne | Corinne | gwenhael | Bug | none | none | Closed | High | 10/01/2012 | 10/16/2012 | gwenhael
e-SMP-3416 | Classif | MS Food classification â€“ Functions: Mass translation & Pagination | 6 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Urgent | 10/1/2012 | 10/5/2012 | Tuan Anh
e-SMP-3417 | Classif | MS Food classification â€“ DATABASE: MS_Classification & MS_Classification_L10N | 8 | Code | Corinne | Corinne | esmp | Evolution | SIGNF | none | To be Affected | Urgent | 10/1/2012 | 10/16/2012 | gwenhael
e-SMP-3419 | Classif | MS Food classification â€“ DATABASE: Questions on Classification | 6 | Code | Corinne | Corinne | Corinne | Note | none | none | Open | Normal | 10/1/2012 | 10/2/2012 | Tuan Anh
e-SMP-3423 | Classif | [Library > CLASSIFICATIONS > Food] pagination | 7 | Others | gwenhael | gwenhael | gwenhael | Q&A | Minor | none | Closed | Normal | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3434 | Classif | [Project > Clasification > Food] cannot remove | 6 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | High | 10/05/2012 | 10/16/2012 | gwenhael
e-SMP-3437 | Classif | [Country > Classification > Food] missing Add / Update/Edit / Delete functions | 8 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/08/2012 | 10/19/2012 | Administrator
e-SMP-3445 | Classif | [Project > Clasification > Food] bypass sub-sub-group creation property | 7 | none | gwenhael | gwenhael | gwenhael | Bug | SIGNF | none | Closed | High | 10/10/2012 | 10/23/2012 | gwenhael
e-SMP-3471 | Classif | [MS > Library Data > CLASSIFICATION>Food Classification] can't remove item | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/16/2012 | 10/23/2012 | Gabriel
e-SMP-3516 | Classif | Classification screens at PROJECT and COUNTRY level | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | WIP | Urgent | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3517 | Classif | Classification screens at PROJECT and COUNTRY level: Special approach for sub-sub-groups | 4 | Code | Corinne | Corinne | gwenhael | Evolution | OPER | none | WIP | Urgent | 10/26/2012 | 10/31/2012 | Tuan Anh
e-SMP-3528 | Classif | [MS > Library data>CLASSIFICATIONS > Food Classification] Deletation summary | 5 | Design / GUI | Gabriel | Gabriel | duydt | Bug | SIGNF | none | Re-Openned | Normal | 10/28/2012 | 11/5/2012 | Tuan Anh
e-SMP-3530 | Classif | [MS > Library data> Food Classification ] Space management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3531 | Classif | [MS > Library data> Food Classification ] Space management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 10/30/2012 | Gabriel
e-SMP-3533 | Classif | FOOD CLASSIFICATION ITEM : error creating food classification | 6 | Code | Philippe | Philippe | Nguyen Xuan Hiep | Bug | OPER | none | Open | Normal | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3534 | Classif | [MS > Library data> Food Classification ] Validating a food classification | 4 | Code | Gabriel | Gabriel | Gabriel | Q&A | OPER | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3535 | Classif | Food classification : copy from a level to an other. | 3 | Code | Philippe | Philippe | gwenhael | Bug | none | none | Open | Normal | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3536 | Classif | [MS > Food classification] Adding food classification item in project level | 5 | Code | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3561 | Classif | [MS > project perimeter ] Adding food classification | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3573 | Classif | MS Food classification: sheet refresh | 2 | Code | Corinne | Corinne | Tuan Anh | Bug | none | none | Open | Normal | 11/6/2012 | 11/6/2012 | Corinne
e-SMP-3455 | EPICTEXT | EPICTEXT : What is this query name * (only numeric) ? | 5 | Code | Philippe | Philippe | gwenhael | Bug | SIGNF | none | Closed | High | 10/14/2012 | 10/16/2012 | gwenhael
e-SMP-3457 | EPICTEXT | EpicText : After 20 entries focus is set on the first page... | 5 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/23/2012 | Philippe
e-SMP-3458 | EPICTEXT | Epictext : Unique Key violation | 4 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3464 | EPICTEXT | Epictext : error while loading... | 6 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3477 | EPICTEXT | [MS > Library data>EpicText] Mass translation | 7 | Spec | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/21/2012 | 10/28/2012 | Gabriel
e-SMP-3418 | Facets/descriptors | [Library > FACETS/DESCRPTORS > Facets] can't validate fiche | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3438 | Facets/descriptors | [Library > FACETS/DESCRPTORS > Facets] error on creation | 4 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/09/2012 | 10/16/2012 | gwenhael
e-SMP-3467 | Facets/descriptors | Facet : my first entrie. | 7 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/14/2012 | 10/17/2012 | Philippe
e-SMP-3470 | Facets/descriptors | [ MS - library / FACETS/DESCRIPTORS>Facet ] Message using green cross to create new item | 8 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Urgent | 10/16/2012 | 10/23/2012 | Gabriel
e-SMP-3475 | Facets/descriptors | [MS > Library data>FACETS DESCRIPTOR] Problem to add an item | 3 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/21/2012 | 10/23/2012 | Gabriel
e-SMP-3476 | Facets/descriptors | FACET & DESCRIPTOR : What is this zone [Raw cooked category] | 2 | Design / GUI | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/21/2012 | 10/28/2012 | Philippe
e-SMP-3498 | Facets/descriptors | [ MS - library / FACETS/DESCRIPTORS BY GROUP ] Error message in PROJECT perimeter | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3503 | Facets/descriptors | [Project > Facet/Descriptors] shouldn't be able to create facet | 7 | Spec | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3504 | Facets/descriptors | Facets & descriptors : fiche & Group field | 3 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Open | Normal | 10/25/2012 | 10/26/2012 | Tuan Anh
e-SMP-3506 | Facets/descriptors | Facets & descriptors : LISTE | 3 | Code | Corinne | Corinne | Corinne | Bug | none | none | Open | Normal | 10/25/2012 | 10/30/2012 | Corinne
e-SMP-3507 | Facets/descriptors | Facets & descriptors: Fiche & default for â€œMulti-selection of descriptorsâ€ field | 5 | Code | Corinne | Corinne | Corinne | Evolution | Minor | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3509 | Facets/descriptors | Facets & descriptors: List and add function | 5 | Code | Corinne | Corinne | Corinne | Bug | SIGNF | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3510 | Facets/descriptors | Facets & descriptors: Fiche descriptor &default for â€œwith limitation for ingredientâ€¦â€ field | 6 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3511 | Facets/descriptors | Facets & descriptors: Descriptor Fiche & â€œraw to cooked categoryâ€ field | 5 | Code | Corinne | Corinne | Corinne | Bug | Minor | none | Reviewed | Normal | 10/25/2012 | 11/2/2012 | Tuan Anh
e-SMP-3512 | Facets/descriptors | Facets & descriptors: Descriptor Fiche & descriptor Type field | 4 | Code | Corinne | Corinne | Corinne | Q&A | none | none | Open | Normal | 10/25/2012 | 10/26/2012 | Tuan Anh
e-SMP-3513 | Facets/descriptors | [MS > Library data>Facet/Descriptor by group] System hangs adding a new facets / descriptor | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/25/2012 | 11/4/2012 | Gabriel
e-SMP-3524 | Facets/descriptors | [MS > PROJECT level / Add facet descriptor] Anormal sort | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | Minor | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3539 | Facets/descriptors | "Facet/descriptor list" screen at country level | 6 | Code | Corinne | Corinne | Corinne | Invalid | Minor | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3540 | Facets/descriptors | Facets/descriptors at Project level: Add new item function (green cross) | 5 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3541 | Facets/descriptors | Facets/descriptors at Library level: Error message | 6 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Urgent | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3542 | Facets/descriptors | Facets/descriptors at Library level: Buttons with work in Mass | 5 | Code | Corinne | Corinne | Tuan Anh | Evolution | OPER | none | WIP | Normal | 10/29/2012 | 11/6/2012 | Corinne
e-SMP-3543 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: add function and field Facets-Descriptors | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3544 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: Add button | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3545 | Facets/descriptors | Facet/descriptor list at Project level: Non validated Facets and attached descriptors | 5 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3546 | Facets/descriptors | Facet/descriptor at Project level â€“ Fiche | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | WIP | Normal | 10/29/2012 | 10/31/2012 | Tuan Anh
e-SMP-3549 | Facets/descriptors | Facets/descriptors by groups/subgroups at Project level: Liste/Fiche and order | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/30/2012 | 11/2/2012 | Tuan Anh
e-SMP-3565 | Facets/descriptors | [MS > project perimeter ] Add facets / descriptors | 5 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3453 | FCO | FCO List : Problem modifying an entrie [LEVEL Livrary] | 6 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3436 | Food list | [MS > Food Update] Abnormal error message | 7 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Closed | High | 10/05/2012 | 10/28/2012 | Gabriel
e-SMP-3444 | Food list | [MS / Food list] abnormal exception | 7 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/09/2012 | 10/16/2012 | gwenhael
e-SMP-3446 | Fractions | (global) fraction management | 8 | none | gwenhael | gwenhael | gwenhael | Note | OPER | none | Closed | High | 10/11/2012 | 10/23/2012 | gwenhael
e-SMP-3424 | Gal | (design) focus in forms | 4 | Others | gwenhael | gwenhael | gwenhael | Note | OPER | none | Closed | Normal | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3425 | Gal | (design) downloading files | 5 | Others | gwenhael | gwenhael | gwenhael | Note | Minor | none | Closed | Low | 10/01/2012 | 10/8/2012 | gwenhael
e-SMP-3426 | Gal | (design) deleting records | 6 | Others | gwenhael | gwenhael | esmp | Evolution | Minor | none | Open | Normal | 10/1/2012 | 10/16/2012 | gwenhael
e-SMP-3427 | Gal | (design) deleting records | 1 | Others | gwenhael | gwenhael | Tuan Anh | Q&A | Minor | none | Closed | Normal | 10/01/2012 | 10/1/2012 | gwenhael
e-SMP-3432 | Gal | [MS > Send Alert] Screen is fixed | 3 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/05/2012 | 10/9/2012 | Gabriel
e-SMP-3435 | Gal | (design) Send Alert: missing scrollbar in recipient list | 6 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/05/2012 | 10/16/2012 | gwenhael
e-SMP-3443 | Gal | [MS > Library Data] Abnormal default selection | 7 | Design / GUI | Gabriel | Gabriel | Corinne | Evolution | SIGNF | none | To be Affected | Normal | 10/9/2012 | 10/26/2012 | Tuan Anh
e-SMP-3474 | Gal | Blue cross function (Iport) | 3 | Spec | Corinne | Corinne | Corinne | Q&A | OPER | none | To be Affected | Normal | 10/19/2012 | 10/31/2012 | Tuan Anh
e-SMP-3479 | Gal | Function blue cross and pagination | 5 | Spec | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3481 | Gal | Control button | 5 | Code | Corinne | Corinne | Corinne | Note | none | none | Reviewed | Normal | 10/21/2012 | 10/26/2012 | Tuan Anh
e-SMP-3482 | Gal | MASS translation - Column Sort | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/21/2012 | 10/22/2012 | Tuan Anh
e-SMP-3483 | Gal | MASS translation â€“ Default Status | 4 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/21/2012 | 10/23/2012 | Tuan Anh
e-SMP-3485 | Gal | [(Food screens)] 'Filter' button in Filters popups | 7 | Design / GUI | gwenhael | gwenhael | gwenhael | Note | Minor | none | Closed | Low | 10/22/2012 | 10/26/2012 | gwenhael
e-SMP-3490 | Gal | Tooltip for Status: missing labels | 5 | Code | Corinne | Corinne | Corinne | Bug | none | none | Reviewed | Normal | 10/22/2012 | 10/25/2012 | Tuan Anh
e-SMP-3491 | Gal | Import data / Import Table: Proposed Perimeter | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | Open | Normal | 10/22/2012 | 10/24/2012 | gwenhael
e-SMP-3493 | Gal | [(Food screens)] groups becoming inactive | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/22/2012 | 10/23/2012 | gwenhael
e-SMP-3494 | Gal | Controls and export files | 2 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/23/2012 | 10/23/2012 | Tuan Anh
e-SMP-3497 | Gal | [MS / framework ] keyboard management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3502 | Gal | [(Food screens)] default selection too wide | 6 | Spec | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3505 | Gal | (GUI) action bar' icons above list content | 7 | Design / GUI | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Normal | 10/25/2012 | 11/5/2012 | gwenhael
e-SMP-3515 | Gal | Info column in all lists and some pop-up | 3 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | WIP | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3519 | Gal | [(Food screens)] classification independent sort | 4 | Code | gwenhael | gwenhael | gwenhael | Evolution | OPER | none | Open | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3520 | Gal | [(Food screens)] classification selection | 4 | Spec | gwenhael | gwenhael | gwenhael | Evolution | Minor | none | Open | Normal | 10/26/2012 | 10/29/2012 | Tuan Anh
e-SMP-3529 | Gal | [MS > Library Data] Input problem with International labels | 5 | Design / GUI | Gabriel | Gabriel | Nguyen Xuan Hiep | Bug | SIGNF | none | Open | Urgent | 10/28/2012 | 10/29/2012 | Tuan Anh
e-SMP-3532 | Gal | [MS > Library data> PROJECT perimeter ] Error message with import data | 4 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3547 | Gal | Project data and Refresh / Country data and refresh | 5 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/29/2012 | 11/2/2012 | Tuan Anh
e-SMP-3550 | Gal | [(Food screens)] classification column should be foldable | 5 | Spec | gwenhael | gwenhael | gwenhael | Evolution | Minor | none | WIP | Normal | 10/30/2012 | 10/31/2012 | Tuan Anh
e-SMP-3560 | Gal | [MS > library perimeter ] Mass translation management | 4 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | High | 11/4/2012 | 11/5/2012 | Nguyen Xuan Hiep
e-SMP-3567 | Gal | [IM > scroll bar] Problem with mouse wheel | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/6/2012 | Tuan Anh
e-SMP-3569 | Gal | [MS > GUI] Page management | 5 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Q&A | OPER | none | Reviewed | Low | 11/4/2012 | 11/5/2012 | Do Hang
e-SMP-3570 | Gal | [MS] mail management | 2 | Others | Gabriel | Gabriel | gwenhael | Q&A | SIGNF | none | Open | High | 11/4/2012 | 11/4/2012 | Gabriel
e-SMP-3409 | HHM | [Library > Photos > HHM] conflicting mandatory fields | 4 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3410 | HHM | [Library > Photos > HHM] missing fraction data | 2 | Others | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | Normal | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3527 | HHM | [MS > Library Data] HHM error management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3562 | HHM | [MS > Library Data] HHM error management | 4 | Code | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | Reviewed | High | 11/4/2012 | 11/6/2012 | Do Hang
e-SMP-3563 | HHM | [MS > country perimeter ] Country code management | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | WIP | Normal | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3487 | Interviewer | Interviewer: Fiche & region | 4 | Code | Corinne | Corinne | Corinne | Bug | OPER | none | Reviewed | Normal | 10/22/2012 | 10/23/2012 | Tuan Anh
e-SMP-3488 | Interviewer | Interviewer list: Unicity | 5 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/22/2012 | 11/2/2012 | Tuan Anh
e-SMP-3489 | Interviewer | Interviewer: Serach | 4 | Code | Corinne | Corinne | Corinne | To be affected | none | none | WIP | Normal | 10/22/2012 | 10/23/2012 | Tuan Anh
e-SMP-3552 | Interviewer | [MS > country perimeter ] Interviewer management | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Low | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3557 | Interviewer | [MS > country perimeter ] Interviewer management | 2 | Others | Gabriel | Gabriel | Gabriel | Bug | Minor | none | Open | Low | 11/4/2012 | 11/5/2012 | gwenhael
e-SMP-3558 | Interviewer | [IM > Country perimeter] Focus problem creating Interviewer record | 3 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/5/2012 | Tuan Anh
e-SMP-3559 | Interviewer | [MS > country perimeter ] Interviewer page management | 4 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | Urgent | 11/4/2012 | 11/5/2012 | duydt
e-SMP-2675 | Iteal | Need to update MS_PROBQUE table. | 2 | Spec | hieuphan | hieuphan | Tuan Anh | Evolution | OPER | none | Closed | High | 2012-06-04 | 5/4/2012 | Tuan Anh
e-SMP-2682 | Iteal | MS-NUTLIMIT: bugs in spec | 3 | Spec | duydt | duydt | duydt | Bug | OPER | none | Closed | High | 2012-06-04 | 6/13/2012 | Tuan Anh
e-SMP-2882 | Iteal | Rawcook | 2 | Code | Tuan Anh | Tuan Anh | Tuan Anh | Q&A | OPER | none | Closed | Urgent | 2012-05-05 | 10/19/2012 | Administrator
e-SMP-3310 | Iteal | MSapp_screen_Improb_descriptors - Rule 8 | 2 | Spec | Tuan Anh | Tuan Anh | Tuan Anh | Q&A | OPER | none | Closed | High | 2012-03-07 | 7/3/2012 | Tuan Anh
e-SMP-3501 | Iteal | Combox: can not Alt +down | 2 | Code | Do Hang | Do Hang | Do Hang | Bug | Minor | none | Closed | Normal | 10/25/2012 | 10/25/2012 | Do Hang
e-SMP-3537 | Maximum | [MS > country perimeter / Add food maximum ] Max value management | 6 | Design / GUI | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | Closed | Low | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3439 | Menu | [MS > Library Data] Menu problem with bulgarian user.. | 6 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | Closed | Urgent | 10/09/2012 | 10/26/2012 | gwenhael
e-SMP-3468 | Menu | all M&S screens not available | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/16/2012 | 10/23/2012 | gwenhael
e-SMP-3486 | Menu | Menu scrollbar | 4 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Reviewed | Normal | 10/22/2012 | 10/26/2012 | Tuan Anh
e-SMP-3518 | Menu | (GUI) wrong content displayed | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/26/2012 | 11/5/2012 | gwenhael
e-SMP-3420 | Nut Limit | [Library > SETTINGS > Internal parameters > Nutrients limitations] Missing values for Unit and Name | 3 | Others | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3442 | Nut unit | Problem with Nutrient unit. | 5 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | Closed | Normal | 10/09/2012 | 10/25/2012 | Philippe
e-SMP-3422 | Nutrient | [Library > SETTINGS > Internal parameters > Nutrients list] Missing values for Unit | 2 | none | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/2/2012 | gwenhael
e-SMP-3572 | Param ES | GUI : EpicSoft Parameters. | 6 | Design / GUI | Philippe | Philippe | Tuan Anh | Bug | OPER | none | Reviewed | Normal | 11/4/2012 | 11/5/2012 | Do Hang
e-SMP-3412 | Photo | [Library > Photos > Photos Series] superfluous check | 5 | Code | gwenhael | gwenhael | gwenhael | Bug | Minor | none | Closed | Low | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3478 | Photo | [MS > Library Data>PHOTOS] Mass update comment & status | 4 | none | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | High | 10/21/2012 | 10/23/2012 | Gabriel
e-SMP-3526 | Photo | [MS > Library data> PHOTOS ] Update photo serie record | 4 | Code | Gabriel | Gabriel | gwenhael | Bug | SIGNF | none | WIP | Normal | 10/28/2012 | 10/30/2012 | Tuan Anh
e-SMP-3566 | Photo | [MS > Library Data] Photo management | 6 | Design / GUI | Gabriel | Gabriel | Do Hang | Bug | SIGNF | none | Corrected | High | 11/4/2012 | 11/5/2012 | duydt
e-SMP-3568 | Photo | [MS > library perimeter ] Silverlight crash when creating a big serie of photos | 4 | Design / GUI | Gabriel | Gabriel | Tuan Anh | Bug | SIGNF | none | WIP | High | 11/4/2012 | 11/6/2012 | duydt
e-SMP-3447 | Probing | [Library > SETTINGS > Probings List] invalid type management | 4 | Spec | gwenhael | gwenhael | Tuan Anh | Bug | SIGNF | none | Closed | High | 10/11/2012 | 10/21/2012 | Gabriel
e-SMP-3448 | Probing | Type of probing... How to set correct values has Checklist | 3 | none | Philippe | Philippe | Philippe | Bug | none | none | Closed | High | 10/14/2012 | 10/25/2012 | Philippe
e-SMP-3449 | Probing | Insert probing : from 2 seconds to 1 minut to commit one probing. | 5 | Code | Philippe | Philippe | gwenhael | Bug | OPER | none | WIP | Normal | 10/14/2012 | 10/17/2012 | Tuan Anh
e-SMP-3450 | Probing | problem of page location when adding all probings... | 5 | Design / GUI | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/28/2012 | Philippe
e-SMP-3496 | Probing | [MS > Library Data] Page management in probing screen | 4 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | Normal | 10/23/2012 | 10/28/2012 | Gabriel
e-SMP-3551 | Probing | [MS > Library data> Probing ] Mass translation over probing | 5 | Code | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3508 | RawToCook | Raw to Cook Gategory screen: Same values twice | 4 | Code | Corinne | Corinne | Corinne | Evolution | OPER | none | Open | Normal | 10/25/2012 | 10/31/2012 | Tuan Anh
e-SMP-3431 | SpDiet | [MS / Special diets] abnormal exception | 6 | Code | Gabriel | Gabriel | Gabriel | Bug | OPER | none | Closed | High | 10/04/2012 | 10/9/2012 | Gabriel
e-SMP-3538 | Std Unit | [MS > country perimeter / tab management ] unknow screen management result (after "Standard unit" menu selection) | 5 | Design / GUI | Gabriel | Gabriel | Gabriel | Bug | SIGNF | none | Closed | Normal | 10/28/2012 | 11/4/2012 | Gabriel
e-SMP-3463 | Substit | Substit table : error after loading. | 7 | Code | Philippe | Philippe | Philippe | Bug | OPER | none | Closed | Normal | 10/14/2012 | 10/18/2012 | Gabriel
e-SMP-3554 | Substit | Substite Table : Level Library = Validated Nothing on project level. | 5 | Code | Philippe | Philippe | Philippe | Bug | SIGNF | none | Closed | Normal | 10/30/2012 | 11/4/2012 | Philippe
e-SMP-3556 | Substit | [MS > Project perimeter / Add subtituable record ] Abnormal records | 5 | Code | Gabriel | Gabriel | Gabriel | Invalid | SIGNF | none | WIP | High | 10/30/2012 | 11/4/2012 | Gabriel
e-SMP-3407 | Thickness | [Library > Photos > Thickness] exception | 4 | Code | gwenhael | gwenhael | gwenhael | Bug | OPER | none | Closed | High | 10/01/2012 | 10/9/2012 | gwenhael
e-SMP-3571 | Translation GUI | [SC > Administration ] Language management | 4 | Others | Gabriel | Gabriel | Gabriel | Q&A | SIGNF | none | WIP | Low | 11/4/2012 | 11/5/2012 | Tuan Anh